## Slide 1: The ERP programme is on budget but six weeks late; two decisions keep go-live in Q1
STEERING COMMITTEE · Q3 2026
Status, risks and two decisions needed today
Programme office · 7 October 2026

## Slide 2: Delivery is recoverable if we decide on data migration scope today
SUMMARY
Decision requested: Approve the reduced migration scope and the second rehearsal budget of €0.4M
1
Spend is 2% under plan at €18.4M of €31M
Forecast at completion holds at €30.6M including contingency.
2
Data migration is six weeks behind the plan
Legacy customer records need more cleansing than estimated.
3
Two decisions protect a Q1 2027 go-live
Narrow migration scope and add a second cut-over rehearsal.
Illustrative data. Source: Programme office status report, 30 Sep 2026
Notes: [Sources]
- Programme office status report, 30 Sep 2026 — illustrative data

## Slide 3: Budget and benefits are on track; schedule is the one red flag
STATUS
Spent to date
Schedule slip
Test cases passed
Open high risks
€18.4M
−2% vs plan
Of €31M approved budget
6 wks
+4 wks QoQ
Driven by data migration
82%
+11 pts
Target 95% before cut-over
3
−2 QoQ
All with owners and dates
Illustrative data. Source: Programme office status report, 30 Sep 2026
Notes: [Sources]
- Programme office status report, 30 Sep 2026 — illustrative data

## Slide 4: Migration now ends in December; cut-over holds if the rehearsal is added
STATUS
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Today
Build and configure
Complete
Data migration
+6 weeks
Testing
SIT and UAT
Cut-over rehearsals
R1
R2
Go-live
Go-live
Illustrative data. Source: Programme office status report, 30 Sep 2026
Notes: [Sources]
- Programme office status report, 30 Sep 2026 — illustrative data

## Slide 5: Narrowing migration scope is the only option that protects the Q1 go-live
DECISIONS
Verdict: Narrow scope keeps go-live in Q1 for €0.4M; older records stay searchable in the archive
Migrate everything
All records since 2012
RECOMMENDED
Narrow scope
Active customers, last 5 years
Delay go-live
Move to Q2 2027
Go-live date
Q2 2027
Q1 2027
Q2 2027
Extra cost
€1.1M
€0.4M
€1.8M
Business impact
None
Archive query tool for old records
Second budget cycle on legacy ERP
Illustrative data. Source: Programme office status report, 30 Sep 2026
Notes: [Sources]
- Programme office status report, 30 Sep 2026 — illustrative data

## Slide 6: Four actions over the next six weeks get migration back on plan
NEXT STEPS
Next step | Owner | Due
Confirm the reduced migration scope with business owners | Programme director | 14 Oct
Contract the archive query tool | IT procurement | 31 Oct
Schedule the second cut-over rehearsal | Cut-over lead | 15 Nov
Report recovery progress at the November steering committee | Programme office | 4 Nov