## Slide 1: Entering the German mid-market can add €40M revenue by 2028
BOARD DISCUSSION DOCUMENT
Recommendation and phased plan for a decision at the 14 November board meeting
Strategy team · October 2026
Notes: Open with the answer. The board has discussed Germany for two years — today is about a decision, not another option paper.

## Slide 2: Entering Germany now captures a €40M window before two rivals scale
EXECUTIVE SUMMARY
Decision requested: Approve a €6M phase-1 budget and the partner shortlist at this meeting
SITUATION
Our UK mid-market business grew 18% a year since 2022 and now funds itself; the product is proven in a regulated market.
COMPLICATION
Two well-funded competitors are preparing German launches in 2027, and switching costs make early share sticky.
RESOLUTION
Enter Germany in 2027 through a partner-led model, scaling direct sales only after 40 reference clients.
Illustrative data. Source: Northwind management accounts FY2025; Strategy team market model, Oct 2026
Notes: If the board reads only this page, it can make the decision.
[Sources]
- Northwind management accounts FY2025 — illustrative data
- Strategy team market model, Oct 2026 — illustrative data

## Slide 3: The UK business is profitable, growing and ready to fund a second market
WHY CHANGE
Revenue FY2025
Operating margin
Net revenue retention
Free cash flow
€42M
+18% YoY
Mid-market drove 60% of growth
23%
+3.1 pts
Highest in five years
112%
+4 pts
Expansion within existing accounts
€9M
+€2.4M
Covers phase 1 without new capital
Illustrative data. Source: Northwind management accounts FY2025
Notes: [Sources]
- Northwind management accounts FY2025 — illustrative data

## Slide 4: The German mid-market is three times our UK base and still under-served
WHY CHANGE
Addressable mid-market firms, thousands
Chart: 
| UK | Germany | France | Netherlands | Nordics
Firms | 0 | 41 | 0 | 0 | 0
Firms (other) | 14 | 0 | 28 | 9.5 | 12
14
41
28
10
12
Germany is the largest prize
The top vendor holds under 12% share; no one owns the segment yet
Two rivals plan 2027 launches — early references will decide share
Illustrative data. Source: Strategy team market model, Oct 2026
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data

## Slide 5: A partner-led entry beats direct build and acquisition on speed and risk
THE RECOMMENDATION
Verdict: Partner-led keeps €6M at risk with quarterly exit gates and still reaches revenue in 2027
Direct build
Own sales team from day one
RECOMMENDED
Partner-led
Two resellers, direct later
Acquire
Buy a local player
Time to first revenue
18 months
7 months
4 months
Capital at risk
€14M
€6M
€35–45M
Control of customer
Full
Shared in years 1–2
Full
Reversibility
Low — sunk cost
High — exit gates
Very low
Illustrative data. Source: Strategy team market model, Oct 2026; Four comparable SaaS entries into Germany, 2019–2025
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data
- Four comparable SaaS entries into Germany, 2019–2025 — illustrative data

## Slide 6: Partners cut time to first revenue from 18 to 7 months
THE RECOMMENDATION
Months from decision to first recurring revenue, comparable entries
Chart: 
| Partner-led (avg) | Hybrid | Direct build (avg) | Greenfield subsidiary
Months | 7 | 0 | 0 | 0
Months (other) | 0 | 11 | 18 | 22
7
11
18
22
Speed wins the window
Partners bring warm pipelines and local compliance know-how
Seven months puts us live before both rivals launch
Illustrative data. Source: Four comparable SaaS entries into Germany, 2019–2025
Notes: [Sources]
- Four comparable SaaS entries into Germany, 2019–2025 — illustrative data

## Slide 7: Germany adds €40M by 2028 on top of a growing UK base
THE RECOMMENDATION
Revenue bridge FY2025 → FY2028, €M
Chart: 
| FY2025 | UK growth | Germany partners | Germany direct | Price changes | Churn | FY2028
Base | 0 | 42 | 73 | 101 | 113 | 108 | 0
Increase | 0 | 31 | 28 | 12 | 4 | 0 | 0
Increase (below zero) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Decrease | 0 | 0 | 0 | 0 | 0 | 9 | 0
Decrease (below zero) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 42 | 0 | 0 | 0 | 0 | 0 | 108
42
+31
+28
+12
+4
−9
108
Germany is 40% of new revenue
€28M of the €40M comes through partners in years 1–2
Direct sales add €12M only after Gate 2
Illustrative data. Source: Strategy team market model, Oct 2026
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data

## Slide 8: Localisation is the critical path; direct sales scale only after Gate 2
HOW WE GET THERE
Q4 26
Q1 27
Q2 27
Q3 27
Q4 27
Q1 28
Today
Partner selection
Shortlist → sign
Localisation
Critical path
Pilot clients
15 references
Gate reviews
Gate 1
Gate 2
Direct sales
Scale
Illustrative data. Source: Strategy team market model, Oct 2026
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data

## Slide 9: Three risks matter most, and each has an owner and an early signal
HOW WE GET THERE
Risk | Likelihood | Impact | Mitigation | Owner
Partners under-deliver pipeline | Medium | High | Two partners with quarterly targets and exit clauses | Strategy
Localisation slips past Q2 2027 | Medium | High | Dedicated squad; scope frozen at German UI and hosting | Product
Rivals undercut on price | High | Medium | Lead on compliance and service; price floor agreed with CFO | Sales
Illustrative data. Source: Strategy team market model, Oct 2026
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data

## Slide 10: Decision today: approve phase 1 so partners can be signed by January
DECISION
DECISION REQUESTED
Approve the €6M phase-1 budget and the shortlist of two German partners
1
Sign letters of intent with the two shortlisted partners
Strategy · 28 Nov
2
Stand up the localisation squad and freeze scope
Product · 5 Dec
3
Register the German entity and open accounts
Finance · 19 Dec
4
First quarterly gate review with the board
CEO · Mar 2027
Illustrative data. Source: Strategy team market model, Oct 2026
Notes: [Sources]
- Strategy team market model, Oct 2026 — illustrative data

## Slide 11: Questions and discussion
Appendix with market model and partner profiles available on request
strategy@northwind.example